## Sprint Backlog (version 1.0)
Sprint Backlog
User Story | Tasks
As a user, I want to be able to ask questions to get answers | Build basic web page interface
Create pipeline for input to chatbot
Create acknowledgement response
Create pipeline to return chatbot output
Customize basic styling on web interface page
As an administrator, I would like to organize the database so the bot can find accurate information for responses easier | Design database
Create tables
Create query format for chatbot
As a user, I would like to be welcomed by the chatbot. | Write predetermined welcome messages
Create new instance method of chatbot interface
Reply with random/prefered greeting
As a user, I want to see example questions/input at the beginning of a chat-bot interaction to get a sense as to what the chat-bot is capable off and how I should structure my questions. | Determine possible set of questions
Create UI element for display
Create "help" keyword/command for users
Create "help" response
As a manager, I would like for the bot to properly understand user input. | Create stimulus and response sequence
Create formatting of various response types
Create processing of keywords to aid search
Create default case for unknown questions
As a user, I want to be able to access the chat-bot 24/7 so that I don’t have to wait for assistance. | Create performance metrics to track stability
Create stress tests for various systems
Create logging points for debugging and error correction
Set up automatic backup/restore for database systems
As a database admin, I want to be able to update the database after games or events. | Create administrator page for database updates
Create scraping tool for event pages
As a manager, I would the software to be accessed on multiple devices. | Create tests for different device formats
Customize styling for different device formats
Test compatability with touch screen and desktop environments